# GATEWAYGUARD — WHO DOES WHAT

Companion to the CPM Schedule (Rev 5, 24-Jul-2026)

Dated: 2026-07-24 08:46 EDT

38 calendar days to launch (September 1, 2026)

## 1. The Critical Path — In Plain English

These are the things that, if they slip, push the whole launch back. Everything else has breathing room. Guard these five with your life:

1. The 12 remaining guide pages. The tool links directly to these — no pages, no launch. Zero slack. Start today, 2–3 per session with Claude.

2. The code-signing certificate. The token is assigned but validation is still pending. Nothing gets signed until it clears. Follow up with SignMyCode if it's quiet by Monday.

3. ascii34 → field test → final fix. The build has to be stable and tested on all three machines before it can be signed. This is the longest chain.

4. The EULA attorney review. Call 1 is Monday. Signing the build waits on the license being settled (at least through the refund-policy call).

5. Signing → screenshots → site QA → launch. Once the build is signed, screenshots must match it, the site gets its final QA, and the hash goes live. This is the home stretch and it's all critical.

## 2. What Claude Does (no approval needed to start)

These are things Claude can produce or draft on its own. You review the output, but Claude doesn't need permission to begin the work.

| Task | Notes |
| --- | --- |
| Build ascii34 (.ps1 + .bat) | After a scoping session with you. Follows the build gate — coding standards, playbook audit, all 23 checks. |
| Write the 12 remaining guide HTML pages | Follows website standards + HTML delivery gate. You push each to GitHub and browser-check. |
| Draft download.html | Gumroad link, system requirements, hash placeholder. |
| Triage field-test logs | After you run the build and upload logs. |
| Draft all marketing copy | ACBL pitch, BBO post, forum posts. You approve tone and send. |
| Research questions | Windows Home BitLocker options, Maine law background, competitor checks, technical verification. |
| Draft legal documents | EULA (done), incident response plan, refund policy language — all for attorney review, not final. |
| Rebuild project documents | CPM, test histories, standards docs — complete replacement files for you to upload. |
| Prepare the old-file cleanup list | Claude lists what's superseded; you delete from project knowledge. |

## 3. What Only Bill Can Do

These require a login, a payment, a physical machine, or your personal identity. Claude cannot do these — they're yours alone.

| Task | Why only you |
| --- | --- |
| Push files to GitHub | Your GitHub login. Claude produces the file; you paste and commit. |
| Run the tool on the test machines | Physical Dell / SANDY / IdeaPad. Claude can't touch hardware. |
| Follow up on cert validation | SignMyCode / DigiCert account is yours. Identity verification is personal. |
| Attend LegalZoom attorney calls | Attorney-client relationship is with you. |
| File copyright registrations | LegalZoom dashboard login; you are the copyright claimant. |
| Set Gumroad pricing + listing | Your Gumroad account and payment setup. |
| Plug in the USB adapter / fix SANDY | Physical hardware. |
| Sign the release build | Physical USB token + your PIN. The signing act is yours. |
| Take screenshots of the final build | Runs on your machine, against the signed build. |
| Upload rebuilt docs to project knowledge | Claude's edits to /mnt/project don't persist — you upload the files Claude delivers. |

## 4. What Claude Can Do — But Needs Your Approval First

These are decisions or irreversible steps. Claude can prepare everything and recommend, but will not proceed until you say go.

| Item | Your decision |
| --- | --- |
| ascii34 scope | Which defects and design items go in the build. Claude proposes; you confirm before the build. |
| Feature freeze | When to stop adding and lock the build for signing. |
| Final EULA wording | After the attorney comments — you approve the final text. |
| Refund policy terms | Window and conditions, once the attorney advises. |
| Annual Updates pricing | $12.99 is the working number — you lock it before launch. |
| Marketing launch timing | Whether ACBL / BBO / forum outreach starts before or after Sep 1. |
| Old-file deletions | Claude lists what to retire; you approve before anything is considered gone. |
| Which machine covers which test state | Claude recommends the matrix; you confirm you can run it. |

## 5. This Week — Split View

| Do now (Bill) | Do now (Claude, with you) |
| --- | --- |
| Push guide/index.html to GitHub | Scope ascii34 (session) |
| Follow up on cert validation | Write guide pages 8–10 (session) |
| LegalZoom Call 1 — Mon 10:30 AM | Draft ACBL pitch final |
| Copyright-register the Tool | Prepare old-file cleanup list |
| Sunday: USB adapter → SANDY online | Triage SANDY logs once online |

Rule of thumb: If it needs a login, a payment, a PIN, a signature, or a physical machine — it's yours. If it's drafting, building, researching, or triaging — Claude starts it and you review. If it's a decision or something that can't be undone — Claude prepares it and waits for your go.

End of Document